| Work Breakdown Structure (WBS) A work breakdown structure (WBS) is a key project deliverable that organizes the team's work into manageable sections. Using WBS, the project management has to plan for the schedule, the fixed costs and the functional completeness of the project and assign responsibilities. The WBS helps make this planning consistent and provides for effective project execution. The Importance of WBS - Creating Measurable and Independent Tasks: The main purpose of a WBS is to reduce complicated activities to a collection of tasks. - Assigning Costs to Each Task: Because the WBS tasks are measurable, the project management can assign specific costs to each task. - Track Progress in a Schedule: Because the WBS tasks have clearly defined limits, the project management can determine how advanced the project is by checking which of the tasks are finished. - Define the Scope of the Project: The challenge is to make sure that everything within the project scope is completed without carrying out any extra work. - Fulfill Intended Purposes: A task is only complete when it fulfills its partial function. When all tasks are finished, all the partial functions add up to a fully functional project. - Assign Responsibility for the Tasks: With a WBS, the project management assigns responsibility for each of the tasks. The task manager is responsible for completing the full scope of the project on time, within the budget and with all of its planned functionality intact. - Cope with details - Stay focused - Satisfy stakeholders Defining the Project The purpose of the process is to identify the specific tasks needed to be done in order to produce the project's deliverables. There are 5 steps guide provide a well structured guide: Step 1: Defining the Project Scope Step 2: Establishing Project Priorities Step 3: Creating the Work Breakdown Structure Step 4: Integrating the WBS with the Organization Step 5: Coding the WBS for the Information System Step 1: Defining the Project Scope Project Scope: A definition of the end result or mission of the project—a product or service for the client/customer—in specific, tangible, and measurable terms. Purpose of the Scope Statement: - To clearly define the deliverable(s) for the end user. - To focus the project on successful completion of its goals. - To be used by the project owner and participants as a planning tool and for measuring project success. - To define the scope of the project, identify the following: - Project objectives - Goals - Sub-phases - Tasks; - Resources - Budget - Schedule. - Project Scope Checklist 1. Project objectives; Overall goal; what, when, how much. 2. Deliverables; Major expected outputs. 3. Milestones; Natural and significant events; time, cost, resources. 4. Technical requirements; To assure performance. 5. Limits and exclusion; Avoid false expectations. 6. Reviews with costumers; Understanding and agreement of expectations. - Terms and Definitions - Scope Statements: Also called statements of work (SOW) - Project Charter - Can contain an expanded version of scope statement - A document authorizing the project manager to initiate and lead the project. - Scope Creep: The tendency for the project scope to expand over time due to changing requirements, specifications, and priorities | Step 2: Establishing Project Priorities - Quality of the project are defined as meeting or exceeding expectations of customer in terms of - Cost (Budget) - Time (Schedule) - Performance (Scope) - One of primary jobs of a project manager is to manage trade-offs among time, cost and performance. - One technique found in practice that is useful for this purpose is completing a priority matrix for the project to identify which standard is constrained, which should be enhanced, and which can be accepted: - Constrain: a parameter is a fixed requirement. - Enhance: optimizing a parameter over others. - Accept: For which standard is it tolerable not to meet the original parameters? Example: Project Priority Matrix (Development of a new wireless modem) Step 3: Creating the Work Breakdown Structure - Work Breakdown Structure (WBS) - An hierarchical outline (map) that identifies the products and work elements involved in a project - Defines the relationship of the final deliverable (the project)to its sub deliverables, and in turn, their relationships to work packages - Best suited for design and build projects that have tangible outcomes rather than process – oriented projects Hierarchical Breakdown of the WBS Level; Hierarchical Breakdown; Description. 1; Project; Complete project. 2 3; Deliverable; Major deliverables. Sub deliverable; Supporting deliverables. 4 5; Lowest sub deliverable; Lowest management responsibility level. Cost account*; Grouping of work packages for monitoring progress and responsibility. Work package; Identifiable work activities. Why Create the WBS? WBS helps the PM by - Facilitating evaluation of cost, time, and technical performance of the organization on a project - Providing management with information appropriate to each organizational level - Helping in the development of the organization break down structure (OBS), which assigns project responsibilities to organizational units and individuals - Helping manage plan, schedule, and budget - Defining communication channels and assists in coordinating the various project elements | Work Packages A work package is the lowest level of the WBS. It is output-oriented in that it: - Defines work (what) - Identifies time to complete a work package (how long) - Identifies a time-phased budget to complete a work package (cost) - Identifies resources needed to complete a work package (how much) - Identifies a single person responsible for units of work (who) Step 4: Integrating the WBS with the Organization Organizational Breakdown Structure (OBS) - Depicts how the firm is organized to discharge its work responsibility for a project - Provides a framework to summarize organization work unit performance - Identifies organization units responsible for work packages - Ties the organizational units to cost control accounts Integration of WBS and OBS Step 5: Coding the WBS for the Information System WBS Coding System - Input to the organizations Information System - Defines: - Levels and elements of the WBS - Organization elements - Work packages - Budget and cost information - Allows reports to be consolidated at any level in the organization structure WBS Coding |
| --- | --- | --- |