| Cost Account - The intersection of the WBS and the OBS that is a budgetary control point for the work packages - Used to provide a roll-up (summation) of costs incurred over time by a work package across organization units and levels, and by deliverables. Process Breakdown Structure - Process-Oriented Projects - Are driven by performance requirements in which the final outcome is the product of a series of steps of phases in which one phase affects the next phase - Process Breakdown Structure (PBS) - Defines deliverables as outputs required to move to the next phase - Checklists for managing PBS: - Deliverables needed to exit one phase and begin the next - Quality checkpoints for complete and accurate deliverables - Sign-offs by responsible stakeholders to monitor progress PBS for Software Project Development Responsibility Matrices - Responsibility Matrix (RM) also called a linear responsibility chart - Summarizes the tasks to be accomplished and who is responsible for what on the project - Lists project activities and participants - Clarifies critical interfaces between units and individuals that need coordination - Provide an means for all participants to view their responsibilities and agree on their assignments - Clarifies the extent or type of authority that can be exercised by each participant Responsibility Matrix for the Conveyor Belt Project Project Communication Plan - What information needs to be collected? - Who will receive information? - What information methods will be used? - What are the access restrictions? - When will information be communicated? - How will information be communicated? | Developing the Project Network Project Network: A flow chart that graphically depicts the sequence, interdependencies, and start and finish times of the project job plan of activities that is the critical path through network. - Provides the basis for scheduling labor and equipment - Provide an estimate of the project’s duration - Provide a basis for budgeting cash flow - Highlights activities that are “critical” and should not be delayed - Help managers get and stay on plan - Logical sequence of work package - Interdependency identify - Identify the longest path through the network is called critical path Terminology Activity: For project managers, an activity is an element of the project that requires time. It may or may not require resources. Typically an activity consumes time—either while people work or while people wait. Ex (wait). Time waiting for contracts to be signed, materials at arrive, budget clearance. Event: A point in time when an activity is started or completed. It does not consume time. Path: A sequence of connected, dependent activities. Merge Activity: An activity that has two or more preceding activities on which it depends. (more than one dependency arrow flowing to it) Parallel Activity: Activities that can take place at the same time and can occur independently if desire, not at the same time. Burst Activity: An activity that has more than one activity immediately following it (more than one dependency arrow flowing from it) Merge (D); Burst (A); Parallel (A, B, C). Critical Path: The longest path through the activity network that allows for the completion of all project-related activities. It is also the shortest expected time in which the entire project can be completed. Delays on the critical path will delay completion of the entire project. Basic Rules to Follow in Developing Project Networks - Networks typically flow from left to right. - An activity cannot begin until all of its activities are complete. - Arrows indicate precedence and flow and can cross over each other. - Identify each activity with a unique number; this number must be greater than its predecessors. - Looping is not possible - Conditional statement are not allowed - Used common start and stop nodes. Free Slack - The amount of time an activity can be delayed without delaying connected successor activities. - Tends to happen as the last activity in a path before a merge activity ( when another path is the critical one) - The term is used primarily in the Critical Path Method where a project’s critical activities are plotted on a timeline. - Free slack or free float therefore shows a task’s schedule flexibility, indicating how long before the next sequential task becomes delayed. | In the part above we have Deliverable, and below – Activity Breakdown Structures Let’s build our Deliverable-Activity Breakdown Structure in matrix form on the basis of both of these hierarchical structures. In the next, discuss how can build project schedule without manually placing links between the tasks. |
| --- | --- | --- |